IT Project Status — January 2015

# Report to the Administration & Finance Committee of the ARRL Board of Directors

The status of the IT projects identified in the ARRL 2014-2015 & 2015-2016 Plans are summarized in Table 1 (below).

During the second half of 2014, web applications software development efforts were directed towards those projects identified in the ARRL 2014-2015 Plan as being of high priority, specifically:

- Centennial Operating Event (Centennial QSO Challenge Points Award  & W1AW Portable Worked All States Award)

This is a holdover project — from the 2013-2014 Plan. Progress towards completion of this project awaited receipt of final, detailed specifications from FSR (nee MVP).  Upon receiving  the approved requirements (on 1/9/15), a detailed Estimate to Complete (ETC) for the remaining work was prepared indicating 332 hours (8.9 weeks) of effort are necessary before “going live”

- AIS Wholesale Publications & Advertising Module

  - Wholesale Publications — Completed acceptance testing with internal customer. Deployed to production.

  - Advertising — Completed coding and system test. Began acceptance testing with internal customer.

- AIS Membership & Subscriptions Module

Continue conceptual design and requirements collection from stakeholders.

- Replacement for DXCC system

Completed detailed design. Held critical design review (CDR). Coding and unit test under way.

Subsequent to the addition of two (2) new Principal Software Engineers in Q2 substantial progress has been made in reducing Logbook of the World’s “technical debt”. Specifically, the database class library has now been re-coded to employ the ODBC (Open Database Connectivity) API rather than existing SAP proprietary API design. Regression testing of the new class library is underway. Moving from the SAP API is a prerequisite for upgrading the Logbook database to the latest, supported release of SAP’s MaxDB RDBMS

In the infrastructure (hardware) area, the following projects were completed:

- Deployed a high-performance database server to production to address the lack of responsiveness (performance) of the ARRL web site.

- Completed an upgrade of networking infrastructure for ARRL HQ LAN.

- Deployed severs and ancillary hardware necessary to create a duplicate of the Logbook of the World system. The LoTW development team has been using this hardware as a software engineering and development test-bed. The same hardware package will be used to support the final scoring of the Centennial QSO Party prior to its eventual deployment to an offsite co-location facility in Q2 2015.

As has been the case for the past several years, the 2015-2016 ARRL Plan over commits the available development resources—in particular the web development resources – by a factor of 2×. This is the definition of a “zero-sum” game wherein progress on any given project can only be made by delaying progress on other projects.

This situation is entirely a consequence of the substantial amount of “technical debt” that accumulated, in some cases for more than a decade. That debt is most concretely represented by the legacy systems such as Siebel and DXCC which are now long overdue for replacement.

As has been stated previously in this context:  When you find yourself stuck deep in a hole, the first thing to do is to stop digging. Given finite resources, the most prudent course of action is not to delay paying down this debt any further but rather to focus the resources that we do have at our disposal on the major development projects needed to replace business critical systems. This course of action necessarily limits the organization’s ability to move forward with other projects in a timely fashion until we are “out of the hole.”

Looking forward, the need to commit similar levels of resources (or to identify additional resources) can be anticipated to continue into the near future in order to address the web site which has represented a major source of technical debt since its acquisition.

Table 1 — IT Project Status (January 2015)

Table 1a — Web Application Software Development Projects (January 2015)

| Priority | Project | Phase | Status |  |
| --- | --- | --- | --- | --- |
|  |  |  | Complete | ETC — Effort (person-months) |
| High (2013) | Centennial Operating Event | Construction | 70% | 2 |
| High (2013) | AIS Affiliated Club Module | Construction | 80% | 0.5 |
| High (2014) | AIS Advertising Module | Construction | 80% | 1 |
| High (2015) | AIS Membership/Subscription/Development Module | Inception | 0% | 9 |
| High (2015) | AIS Membership — Web membership application/renewal | Inception | 5% | 3 |
| High (2015) | AIS Membership — Automatic renewal of membership | Inception | 5% | 3 |
| High (2015) | AIS Membership — Account management | Elaboration | 15% | 13 |
| High (2015) | AIS Education Module | Inception | 0% | 4 |
| High (2015) | Replacement for DXCC (“ATS”) system | Construction | 35% | 10 |
| High (2015) | Web service subscription interface for Digital QEX | Inception | 0% | 2 |
| High (2015) | Web service for VEC portal | Inception | 0% | 2 |
| Medium (2014) | Upgrade ARRL web site software components | Elaboration | 10% | 3 |
| Medium (2014) | Improve tools for ARRL electronic newsletters | Inception | 0% | 2 |
| Medium (2014) | Authentication web service for exam generation | Inception | 0% | 2 |
| Medium (2015) | “Contest 2020” Phase 2 | Inception | 0% | 2 |
| Low (2014) | “Contest 2020” Phase 1 | Transition | 60% | 2 |
|  |  |  | Total Effort | 60.5 |
|  |  |  | Available Effort | 23 |
|  |  |  | Commitments | 263% |

Table 1 — IT Project Status (January 2015) – cont.

Table 1b — LoTW Software Development Projects (January 2015)

| Priority |  | Project |  | Phase | Status |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Complete | ETC — Effort (person-months) |
| High (2015) |  | Add new awards (award sponsor API) |  | Inception | 0% | 4 |
| High (2015) |  | Improvements to user interface (Logbook web site redesign) |  | Inception | 0% | 12 |
| High (2015) |  | Update administration and awards management screens |  | Inception | 0% | 6 |
| Medium (2014) |  | Code maintenance and upgrade SAP database classes |  | Construction | 90% | 0.5 |
| Medium (2014) |  | Instrument, monitor and tune database performance |  | Construction | 10% | 2 |
| Medium (2014) |  | Establish a Logbook of the World co-location site. |  | Transition | 90% | 0.50 |
| Medium (2014) |  | Add ARRL 5-Band awards (DXCC & WAS) |  | Construction | 50% | 1 |
|  |  |  |  |  | Total Effort | 26 |
|  |  |  |  |  | Available Effort | 23 |
|  |  |  |  |  | Commitments | 113% |

Table 1 — IT Project Status (January 2015) – cont.

Table 1c — Infrastructure Projects (January 2015)

| Priority |  | Project |  | Phase | Status |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Complete | ETC — Effort (person-months) |
| High (2015) |  | Upgrade MS Great Plains to latest |  | Elaboration | 25% | 0.5 |
| High (2015) |  | Install boundary firewall |  | Elaboration | 15% | 0.5 |
| High (2015) |  | Install perimeter firewall |  | Elaboration | 15% | 0.5 |
| High (2015) |  | Upgrade McAfee anti-virus/anti-malware protection suite |  | Elaboration | 10% | 0.5 |
| High (2015) |  | Deploy McAfee Complete Endpoint Protection module |  | Elaboration | 5% | 0.25 |
| High (2015) |  | Deploy McAfee Web Security module |  | Elaboration | 5% | 0.25 |
| High (2015) |  | Security / vulnerability assessment by external consultant |  | Inception | 10% | 1 |
| High |  | Implement migration plans for Windows Server 2003 servers (4) |  | Construction | 25% | 2 |
| Medium |  | Configure & deploy Network Monitoring Center |  | Construction | 15% | 3 |
| Medium (2015) |  | Deploy McAfee Host Intrusion Prevention s/w |  | Elaboration | 5% | 0.25 |
| Medium (2015) |  | Deploy security policy changes to HQ servers |  | Construction | 75% | 0.5 |
| Low (2014) |  | Upgrade HW desktop systems to MS Office 2013 / Office 365 |  | Inception | 10% | 1 |
| Low (2014) |  | Deploy security policy changes to HQ desktop users |  | Construction | 25% | 2 |
|  |  |  |  |  | Total Effort | 12 |
|  |  |  |  |  | Available Effort | 12.6 |
|  |  |  |  |  | Commitments | 95% |

Table 1 — IT Project Status (January 2015) – cont.

Table 1d —Projects Completed in Q3/Q4 2014

| Priority | Project |
| --- | --- |
| High (2014) | AIS Wholesale Publications Sales & Fulfillment Module |
| High (2014) | AIS Advertising Sales Module |
| High (2014) | Improve ARRL web site performance |
| High (2015) | Upgrade firewall at Warehouse |
| Medium (2014) | ARRL HQ LAN upgrade. |

Figure 1 Software System Design Process