Index of Incomplete Board Actions -- By Meeting  (as of 5 July 2018)

# Summary of Major Board Actions

## Minute	     Purpose							Disposition	Disposition					Target Completion

Now						Date

January 2012

51	Implementation of National Broadband Plan Committee report		EC		Subgroup of EC created September 2012; no

recent progress, re-established 2017			None given

January 2014

50	Additional recommendations of Committee on Youth			Board, staff	Remainder of July 2013 committee report

in the Second Century								recommendations should be considered		None given

July 2014

36	Commitment of resources for new amateurs, more diversity		Staff		First steps are in 2015-2016 plan; some

funding/goals in 2016-2017 plan 			None given

43	Web based reporting system for field volunteer activities		P&SC, staff	First phase to be implemented during 2015		None given

January 2015

30	Volunteer Instructor database given high priority			staff		Specs done; NPOTA moved ahead in priority	Early 2016

January 2016

38	Implement revised travel policy					staff		Pending Directors Wbk update			None given

March 2016 - EC

July 2016

28	Implement a one-time non-endorsable mobile DXCC award		staff								Completed 2/18/18

29	Change MVP to FS&R in Rules/Reg of Field Organization		staff								None given

30	Add paper certificate option to DXCC Honor Roll awards		staff								None given

October 2016 – EC

6	Continue work on new MOU with FCC on enforcement		CEO /W3KD/K4ZDH						Fall 2017

January 2017

17	Implement new Policy on Board Governance			staff								None given

26	Work on five legislative objectives					Board, staff							None given

28	Implement BL 36/38 changes to eliminate CDO COO CTO		Staff								Completed 2017

34	Implement changes to DXCC Field Checking program		Staff								None given

35	Implement recommendations of the Entry Level			Staff, ELL Cte 							None given

License Committee

March 2017 – EC

July 2017

23	Implement new policy on convention approvals			Staff								Completed 2017

25	Review AA&BL							Exec Committee							By 12/31/17, completed

27/29	Updated AA&BL – name/indemnity				Staff								Pending 7/18 Board

28	Implement new Centurian award					Staff								None given

32	Review R&R on Advisory Committees				Exec Committee 							Fall 2018

33	Develop plan to revise Technician privileges				Exec Committee							FCC filing made 2/28/18

Continue research/recommendations for outreach and licensing	Entry Level License Committee					None given

34	Review matching criteria in LoTW					LoTW and PSC Committees					None given

October 2017 - EC

3	Investigate experimental license for 76-81 GHz			General Counsel							None given

4	Evaluation of all membership programs				PSC including coordination with A&F				Fall 2018

4	Draft ByLaw change to develop and implement alternative 		General Counsel							None given
              dispute resolution

5	File a request for declaratory ruling to correct discrepancies		General Counsel							None given

between Part 73 and Part 97

8	Share Day, Pitney concerns with two recent ByLaw changes		Exec Committee							30 day prior Jan 18 board

12	Develop proposal to implement Entry Level license committee		General Counsel, Bellows, Frenaye					Filed 2/28/18, complete

recommendations

January 2018

25	Report to A&F and Board on Mintz & Hoke discovery and 		Staff								by July 2018

strategy phase of Lifelong Learning project

27	CEO Search Committee to report to Board				CEO Search committee						July 2018

41	Changes to BL 8-9-10 referred to A&F for study			A&F Committee							None given

42	Place EC1-11 on web site with white paper				Exec Committee							none given

47	Review Code of Conduct						Officers, Directors, Vice Directors					60 days prior to July 2018

meeting (May 20)

Postponed to late 2018

49	File Technician modernization petition with FCC			Exec Committee 							FCC filing – done 2/28/18

Start dialog with NCVEC on exam goals/process											NCVEC – none specified

April 2018 - EC

5	Prepare motions to add Articles on liability and indemnity		Staff								Pending July 2018 board

6	Prepare motion to modify Article 1 regarding ARRL name		Staff								Pending July 2018 board

7	Prepare motion to update ByLaw 23 				Staff								Pending July 2018 board

8	Create ad-hoc committee to propose revised Code of Conduct		CoC committee, EC						Committee appointed

10	Prepare comments on Spectrum Horizons – 95+ GHz			W3KD, staff, EC							FCC filing – done 5/2/18

11	File comments on small satellites IB Docket 18-86			W3KD, staff, EC							none given

12	File ex parte comments in RM-11785 on  5 MHz request		W3KD, staff							none given

13	Support a request for an STA on 76 GHz				W3KD								none given

16	Allow additional appointments of  OO/OOCs			Staff								none given

TF  7/5/18